## GanttChart
Team Chat (Web App) Project Schedule
| Project Start Date: |  |  | 2015-06-04 | time axis 2015-06-01 to 2015-07-27
| Display Week: |  |  | 1 |  |  |  |  | 2015-06-01: Week 1; 2015-06-08: Week 2; 2015-06-15: Week 3; 2015-06-22: Week 4
[16 empty] | 2015-06-08 | [6 empty] | 2015-06-15 | [6 empty] | 2015-06-22
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Log In
1.1 | Create login view |  |  | 2015-06-04 | 2015-06-04 | 1 | 0% | 0
1.2 | Post login info |  |  | 2015-06-05 | 2015-06-05 | 1 | 0% | 0
1.3 | User Auth |  |  | 2015-06-06 | 2015-06-06 | 1 | 0% | 0
1.4 | Redirect to home or deny |  |  | 2015-06-07 | 2015-06-07 | 1 | 0% | 0
2 | Search for users
2.1 | Post search data |  |  | 2015-06-04 | 2015-06-04 | 1 | 0% | 0
2.2 | Create results view |  |  | 2015-06-05 | 2015-06-05 | 1 | 0% | 0
2.3 | Populate results with query |  |  | 2015-06-06 | 2015-06-06 | 1 | 0% | 0
3 | Send user a msg
3.1 | Create chat view |  |  | 2015-06-04 | 2015-06-04 | 1 | 0% | 0
3.2 | Post msg |  |  | 2015-06-05 | 2015-06-05 | 1 | 0% | 0
3.3 | Update chat log with new msg |  |  | 2015-06-06 | 2015-06-06 | 1 | 0% | 0
4 | Create/Edit group
4.1 | Create view for group management |  |  | 2015-06-07 | 2015-06-07 | 1 | 0% | 0
4.2 | Create view to add/edit group |  |  | 2015-06-08 | 2015-06-08 | 1 | 0% | 0
4.3 | Post group info |  |  | 2015-06-09 | 2015-06-09 | 1 | 0% | 0
4.4 | Update groups list |  |  | 2015-06-10 | 2015-06-10 | 1 | 0% | 0
5 | Send group msg
5.1 | Create view for group chat |  |  | 2015-06-07 | 2015-06-07 | 1 | 0% | 0
5.2 | Post msg |  |  | 2015-06-08 | 2015-06-08 | 1 | 0% | 0
5.3 | Update chat log with new msgs |  |  | 2015-06-09 | 2015-06-09 | 1 | 0% | 0
6 | Share docs
6.1 | Add file upload button to chat views |  |  | 2015-06-07 | 2015-06-07 | 1 | 0% | 0
6.2 | Upload selected doc |  |  | 2015-06-08 | 2015-06-08 | 1 | 0% | 0
6.3 | Display uploaded docs to receivers in chat |  |  | 2015-06-09 | 2015-06-09 | 1 | 0% | 0
7 | Delete group
7.1 | Add a button to delete a group you manage |  |  | 2015-06-10 | 2015-06-10 | 1 | 0% | 0
7.2 | Update groups list when deletion confirmed |  |  | 2015-06-11 | 2015-06-11 | 1 | 0% | 0
8 | Msg notifications
8.1 | Display a popup or icon when a new msg is received |  |  | 2015-06-12 | 2015-06-12 | 1 | 0% | 0
8.2 | Clicking on the popup/icon displays notification details |  |  | 2015-06-13 | 2015-06-13 | 1 | 0% | 0
8.3 | Add link to view new msg |  |  | 2015-06-14 | 2015-06-14 | 1 | 0% | 0
9 | Profile editing
9.1 | Create a profile view |  |  | 2015-06-12 | 2015-06-12 | 1 | 0% | 0
9.2 | Create an edit profile view |  |  | 2015-06-13 | 2015-06-13 | 1 | 0% | 0
9.3 | Add a save button to push updated profile info to database |  |  | 2015-06-14 | 2015-06-14 | 1 | 0% | 0
9.4 | Update profile with new info |  |  | 2015-06-15 | 2015-06-15 | 1 | 0% | 0
10 | Testing and Integration
10.1 | Testing and Integration |  |  | 2015-06-16 | 2015-06-23 | 8 | 0% | 0
10.2 | Integrate with other modules |  |  | 2015-06-17 | 2015-06-24 | 8 | 0% | 0
Note on A6: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B6: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C6: Task Lead Enter the name of the Task Lead in this column.
Note on D6: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E6: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G6: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H6: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I6: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.